## Product Backlog
Product Backlog
Dice Simulator 2016
ID | Feature name | Status | Size | Sprint | Comments
1 | Create a player | Planned | 20 | 3 | Add a new player
2 | Delete player | Removed | 20 |  | Delete an existing player
3 | Update score | Planned | 20 | 3 | Update the scores/stats (like after a game)
4 | Roll 3 dice | Done | 5 | 2
5 | Save score | Planned | 20 | 3 | Save the persistent score/stats
6 | Provide statistics to GUI | Planned | 20 | 3 | Provide statistics about players/games to the GUI
7 | Add player to game | Done | 20 | 2 | Add an existing player to a new game
8 | Start game | Done | 20 | 2 | Start a new game
9 | User pass | Removed | 20 |  | User can pass after they roll
10 | Restart game | Removed | 20 | 3 | Restart a game with the same players
11 | Add nice artwork | Planned | 13 | 3 | Make the GUI look nice
12 | Rule logic in response to rolls | Done | 20 | 2 | Add core game logic that occurs after each roll (e.g. win, lose)
13 | Player management GUI | Done | 40 | 2 | GUI to choose players for a game
14 | Game GUI | Done | 40 | 2 | Main GUI during a game
15 | Player Stats GUI | Planned | 40 | 3 | GUI that displays player/game stats
16 | End game GUI | Planned | 40 | 3 | GUI displayed after a game is over
17 | Rule GUI | Done | 13 | 2 | GUI to display the game rules